## Sheet1
Task ID | Task Name | Assigned To | Due Date | Priority | Progress | Comments | Count Tasks in between 30% to 50%
1 | Design Website Mockup | Wahid Shuvo | 2025-03-30 | High | 100% | Design looks good, need revisions | 4
2 | Write Blog Post | Tomalisha Keya | 2025-03-25 | Medium | 0% |  | Task Assigned to Imtiaj
3 | Implement Analytics | Tashfiya Nowreen | 2025-03-28 | High | 100% | Done successfully | 1
4 | Create Logo | Syed Abrar | 2025-04-05 | High | 30% | Initial concepts approved, need feedback
5 | Update Homepage Content | Shohanur Rahman | 2025-03-27 | Medium | 50% | Writing content for the homepage | Priority High and Completed
6 | Organize Client Meeting | Shihab Alam | 2025-03-29 | Low | 0% | Schedule meeting with client | 2
9 | Develop Mobile App | Shakil Rahman | 2025-05-01 | High | 0% | Initial planning phase
8 | Create Marketing Strategy | Shakil Rahman | 2025-04-10 | High | 0% | Waiting on team feedback | Avearge
7 | Conduct User Research | Shakil Rahman | 2025-04-02 | High | 40% | Conducting interviews | 42.25%
10 | Review Sales Dashboard | Shahriar Sifat | 2025-03-31 | Medium | 70% | Reviewing metrics, refining dashboard
11 | Update Product Catalog | Rakin Rabbani | 2025-04-07 | Medium | 100% | Updated with new products | Filtered by Priority high and Progress 100%
14 | Plan Social Media Campaign | Nure Amin | 2025-04-08 | Medium | 0% | Planning phases
13 | Implement SEO Strategies | Masum Billah | 2025-03-25 | High | 20% | Research phase | Task ID | Priority | Progress
12 | Write Press Release | Maria Nawar | 2025-04-12 | Low | 0% | Drafting the press release | 1 | High | 100%
15 | Test Website on Mobile | Mahmudur Abir | 2025-03-31 | Low | 100% | Website working fine on mobile | 2 | Medium | 0%
16 | Create Email Newsletter | Imtiaj Alam | 2025-04-15 | Medium | 25% | Designing template | 3 | High | 100%
17 | Launch New Feature | Fariha Tamreen | 2025-04-20 | High | 30% | Gathering requirements | 4 | High | 30%
18 | Write User Manual | Faiyaz Binte | 2025-04-03 | Medium | 80% | Writing content, need review | 5 | Medium | 50%
19 | Plan Team Building Event | Arobi Amin | 2025-04-09 | Low | 0% | Finding venue | 6 | Low | 0%
20 | Update Privacy Policy | Anisul Islam | 2025-04-25 | Medium | 100% | Updated for new regulations | 9 | High | 0%
[7 empty] | 8 | High | 0%
[7 empty] | 7 | High | 40%
[7 empty] | 10 | Medium | 70%
[7 empty] | 11 | Medium | 100%
[7 empty] | 14 | Medium | 0%
[7 empty] | 13 | High | 20%
[7 empty] | 12 | Low | 0%
[7 empty] | 15 | Low | 100%
[7 empty] | 16 | Medium | 25%
[7 empty] | 17 | High | 30%
[7 empty] | 18 | Medium | 80%
[7 empty] | 19 | Low | 0%
[7 empty] | 20 | Medium | 100%